## Tasks and Timeline
Sauce & Spoon Project Plan
Task | Notes | Start Date | Due Date | Duration | Task Owner | Status | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
[7 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
Research tablet options |  |  |  | 2
Generate quotes and review costs | consider cybersecurity and data encryption strategies |  |  | 1
Test out tablet packages |  |  |  | 2
Vendor timeline and deliverables schedule |  |  |  | 5
confirm the number of tablets needed |  |  |  | 2
Milestone: Choose a tablet package |  |  |  | 12
shipping for current tablet model |  |  |  | 6
shipping for new tablet model |  |  |  | 21
Schedule an electrician |  |  |  | 1
Create customer survey questions |  |  |  | 1
Connect the marketing department with Terrific Tablets for branding |  |  |  | 1
Update menu interface to match restaurant branding |  |  |  | 4
define a central charging area for the devices |  |  |  | 1
define a central, secure location for storing devices |  |  |  | 1
update POS system | if needed |  |  | 4
integrate tablets with POS software | check that the software needs updating |  |  | 2
Wire up the tablets | schedule 2 half days at each location, check with electrician to see if mornings or afternoons are better, notify GMs about restaurant closing |  |  | 4
new menu from Carter | unpredictable, depends on inspiration |  |  | 5
determine featured menu items and coupon values | dependent on Carter's menu updates |  |  | 1
upload featured menu items and coupon values | dependent on Carter's menu updates |  |  | 1
Milestone: complete tablet installation |  |  |  | 45
draft a training plan |  |  |  | 7
hold a pre-training meeting to introduce tablets to the staff |  |  |  | 1
Train the staff to update the menu |  |  |  | 1
train key staff members at each location on new technology |  |  |  | 1
schedule training sessions for waitstaff at each location on new technology | pre-meeting, manager training, and staff training will need to be on all different days] |  |  | 2
Milestone: complete training |  |  |  | 14
hold a Sunday morning test run - test training, tablets |  |  |  | 1
replace old tablets with new tablets |  |  |  | 3

## Task Brainstorm
Task Brainstorm
Task | Notes | Estimated Duration (Days) | Optimistic | Most Likely | Pessimistic | Confidence Rating (H/M/L) | Known Dates
Research tablet options |  | 2 | 1 | 2 | 2 | H
Generate quotes and review costs | consider cybersecurity and data encryption strategies | 1 | 1 | 1 | 1 | H
Test out tablet packages |  | 2 | 1 | 2 | 3 | M
Vendor timeline and deliverables schedule |  | 5 | 4 | 5 | 6 | M
confirm the number of tablets needed |  | 2 | 1 | 2 | 3 | H | 1st of the month
Milestone: Choose a tablet package
shipping for current tablet model |  | 6 | 4 | 6 | 7 | M
shipping for new tablet model |  | 21 | 14 | 21 | 30 | L
Schedule an electrician |  | 1 | 1 | 1 | 1 | H
Create customer survey questions |  | 1 | 1 | 1 | 1 | H
Connect the marketing department with Terrific Tablets for branding |  | 1 | 1 | 1 | 1 | H
Update menu interface to match restaurant branding |  | 4 | 3 | 4 | 5 | M
define a central charging area for the devices |  | 1 | 1 | 1 | 1 | H
define a central, secure location for storing devices |  | 1 | 1 | 1 | 1 | H
update POS system | if needed | 4 | 3 | 4 | 4 | M
integrate tablets with POS software | check that the software needs updating | 2 | 1 | 2 | 6 | L
Wire up the tablets | schedule 2 half days at each location, check with electrician to see if mornings or afternoons are better, notify GMs about restaurant closing | 4 | 4 | 4 | 6 | H
new menu from Carter | unpredictable, depends on inspiration | 5 | 5 | 8 | 10 | L
determine featured menu items and coupon values | dependent on Carter's menu updates | 1 | 1 | 1 | 1 | H
upload featured menu items and coupon values | dependent on Carter's menu updates | 1 | 1 | 1 | 1 | H
Milestone: complete tablet installation
draft a training plan |  | 7 | 4 | 7 | 10 | M
hold a pre-training meeting to introduce tablets to the staff |  | 1 | 1 | 1 | 1 | M
Train the staff to update the menu |  | 1 | 1 | 1 | 1 | M
train key staff members at each location on new technology |  | 1 | 1 | 1 | 1 | M
schedule training sessions for waitstaff at each location on new technology | pre-meeting, manager training, and staff training will need to be on all different days] | 2 | 2 | 2 | 2 | H
Milestone: complete training |  | 14 | 10 | 14 | 21 | M
hold a Sunday morning test run - test training, tablets |  | 1 | 1 | 1 | 1 | H
replace old tablets with new tablets |  | 3 | 2 | 3 | 5 | H

## Additional Resources
Additional Resources
Title | Link | Date Added | Notes
Tabletop tech speeds up service and boosts profits, study says | https://www.restaurantdive.com/news/tabletop-tech-speeds-up-service-and-boosts-profits-study-says/560152/ | 2021-10-11 | insight on needed strength for cybersecurity and data encryption
Best Practices for Using iPads in the Restuarant Industry | https://www.lockncharge.com/eu/blog/industry-news/best-practices-for-using-ipads-in-the-restaurant-industry/ | 2021-10-11 | tip to remember a central charging station and security for devices

## Quality and Evaluation
Quality and Evaluation
Quality Standards | Quality Standards
Category | Criteria/Description | Evaluation Questions | Evaluation Indicators | Criteria Met?
Ticket Time | 8 minutes for appetizers, 12-15 minutes for entrees | Which goals are being met? | Average time for appetizers and average time for entrees to come out of the kitchen | FALSE
Check Out Experience | hit a check out time of 1 minute or less | What are the most common participant reactions? | Customer surveys showing how satisfied they are with the new dining experience | FALSE
Technical Issues | less than 5% of customers who use the tablets report technical issues each week | What is working and what's not working? | number of dishes sent back to the kitchen | FALSE
Order Accuracy | 98% accuracy |  | average wait time | FALSE
Wait Time | average wait time of 10 minutes or less |  |  | FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE

## Survey Questions
Survey Questions
Quality Standards |  |  |  |  | Question Answer Options (depends on question type)
Criteria/Description | Evaluation Questions | Evaluation Indicators | Survey Question | Question Type | Option #1 | Option #2 | Option #3 | Option #4 | Option #5
8 minutes for appetizers, 12-15 minutes for entrees | Which goals are being met? | Average time for appetizers and average time for entrees to come out of the kitchen | Have you visited Sauce & Spoon before? | Yes/No | Yes | No
hit a check out time of 1 minute or less | What are the most common participant reactions? | Customer surveys showing how satisfied they are with the new dining experience | Did you use a tablet during your recent experience at Sauce & Spoon? | Yes/No | Yes | No
less than 5% of customers who use the tablets report technical issues each week | What is working and what's not working? | number of dishes sent back to the kitchen | How was your overall experience at Sauce & Spoon? | Scaled | Poor | Mediocre | Moderate | Great | Excellent
98% accuracy |  | average wait time | On a scale of 1 to 5, how easy was the tablet to use? | Scaled | 1 | 2 | 3 | 4 | 5
average wait time of 10 minutes or less |  |  | Did you experience any technical difficulties with the tablets? | Open-ended | Yes | No | If yes, please describe.
|  |  | How long did you wait to be seated at a table? | Multiple choice | No wait | Less than 5 minutes | 5-10 minutes | 10-15 minutes | More than 15 minutes
|  |  | How long did you wait for your food? | Multiple choice | 5-8 minutes | 9-12 minutes | 13-16 minutes | More than 16 minutes
|  |  | How long was your check out experience? | Multiple choice | Less than a minute | 1-2 minutes | 3-4 minutes
|  |  | I received the food I ordered | True/False | TRUE | FALSE